## PECI
ĐÍNH KÈM 01: CHI TIẾT KHỐI LƯỢNG VÀ NỘI DUNG CÔNG VIỆC Đính kèm thư mời chào hàng
Stt | Khu vực | Đơn vị | Loại thiết bị | Mô tả công việc | Số lượng | Đơn vị tính | Thời gian thực hiện | Địa điểm | Ghi chú
1 | 4 | 61 | COMPRESSOR | OEM : Burckhardt To do Major overhaul compressor. Major inspection: Main scope is valve, piston, bearing, stuffing box inspection - Install external scaffold. - Arrange special tools and consumables. - Remove Coupling Guard and coupling. - Remove and install instruments. - Suction discharge valve remove, clean, inspect and replace/ reinstall. - Stuffing boxes remove, clean, inspect and replace/ reinstall. - Piston removes, clean, inspect and reinstall. - Bearings and Oil seals remove, clean, inspect and replace/ reinstall. - Alignment checking and record. - Filter and Oil replacement. Clean suction strainer - Remove any external scaffolding. - Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
2 | 4 | 061 | MIXER | - Replace V-belt & lube oil - Checking magnetic driver | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
3 | 4 | 061 | MIXER | OEM : ZUCCHETTI S.r.l. 061-M-301 to do overhaul - Install external scaffold. - Install blinds as per blind list. - Remove Agitator and sends to workshop. - Bearing inspection and replacement. - Shaft inspection. - Mechanical Seal Inspection. - Replace oil. - Replace new seal pump 061-M-301-P01 - Remove blinds as per blind list. - Remove any external scaffolding - Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
4 | 4 | 061 | MIXER | OEM : Dettin SPA, OEM Engineer: No -Install external scaffold. -Remove Coupling Guard and coupling. -Replace the lubricants. - Remove bottom cover, spool 061-V-501 and control valve 061-LV-5001 - Inspection bushing - Remove and inspect, replace packing. -Remove any scaffolding -Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn |  | 0
5 | 4 | 061 | PUMP | OEM : Flowserve, OEM Engineer: Yes 061-P-201 to do overhaul - Install external scaffold. - Arrange special tools and consumables. - Install blinds as per blind list. - Instrument support to remove the sensors if any. - Remove Coupling Guard and coupling. - Disconnect and remove Suction Pump - Remove and inspect, replace Bearing, Mechanical Seal. - Propeller inspection. - Lube oil system flushing & replacement. - Leak test & flushing seal system - Reinstall suction pump and instrument devices. - Measuring parts and final alignment. - Remove blinds as per blind list. - Remove any external scaffolding. - Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
6 | 4 | 061 | PUMP | OEM : Flowserve OEM Engineer: Yes 061-P-201 to do overhaul - Install external scaffold. - Arrange special tools and consumables. - Install blinds as per blind list. - Instrument support to remove the sensors if any. - Remove Coupling Guard and coupling. - Disconnect and remove Suction Pump - Remove and inspect, replace Bearing, Mechanical Seal. - Propeller inspection. - Lube oil system flushing & replacement. - Leak test & flushing seal system - Reinstall suction pump and instrument devices. - Measuring parts and final alignment. - Remove blinds as per blind list. - Remove any external scaffolding. - Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
7 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To inspect (NDT if required) - To replace soft part and hard part if any damage - To pop up test and attach lead seal and tag name. - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
8 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To do calibration and inspection at WS - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
9 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To do calibration and inspection at WS - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
10 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To do calibration and inspection at WS - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
11 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To do calibration and inspection at WS - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
12 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To do calibration and inspection at WS - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
13 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To do calibration and inspection at WS - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
14 | 4 | 061 | EXTRUDER | - Drain Hoil Oil inside Die plate - Replace die plate - Make up Hot Oil | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
15 | 4 | 061 | EXTRUDER | - Drain Hoil Oil inside Die plate - Replace die plate - Make up Hot Oil | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
16 | 4 | 061 | ROTARY FEEDER | OEM : SANKO OEM Engineer: No To do overhaul -Chain and sprocket inspection. -Gland packing replacement. -Rotor inspection. -Bearing inspection and replacement. -Replace oil. -Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
17 | 4 | 061 | ROTARY FEEDER | OEM : SANKO OEM Engineer: No To do overhaul -Chain and sprocket inspection. -Gland packing replacement. -Rotor inspection. -Bearing inspection and replacement. -Replace oil. -Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
18 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To overhaul and inspection (NDT if required) - To replace soft part and hard part if any damage - To pop up test and attach lead seal and tag name. - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
19 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To calibration at ws - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
20 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To calibration at ws - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
21 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - Do calibration at WS - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
22 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - Do calibration at WS - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
23 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To calibration at ws - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
24 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To inspect (NDT if required) - To replace soft part and hard part if any damage - To pop up test and attach lead seal and tag name. - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
25 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - Do calibration at WS - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
26 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - Do calibration at WS - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
27 | 4 | 061 | FEEDER | OEM : Daega Powder OEM Engineer: No To do overhaul -Chain and sprocket inspection. -Gland packing replacement. -Open cover to visual rotor inspection. -Bearing inspection and replacement. -Inspect the lower shaft and blade condition. -Replace oil. -Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
28 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
29 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
30 | 4 | 061 | DRYER | Replace oil, replace bearing, oil seal, belt, air filter and inspection rotor, pulley. OEM : JSW OEM Engineer: No To do overhaul - Install internal and external scaffold. -Remove Coupling Guard and coupling. - Replace the lubricants. - Remove and inspect/replace bearing, oil seal, belt, air filter and inspection rotor, pulley. -Remove any internal and external scaffolding -Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
31 | 4 | 061 | DRYER | Replace oil, replace bearing, oil seal, belt, air filter and inspection rotor, pulley. OEM : JSW OEM Engineer: No To do overhaul - Install internal and external scaffold. -Remove Coupling Guard and coupling. - Replace the lubricants. - Remove and inspect/replace bearing, oil seal, belt, air filter and inspection rotor, pulley. -Remove any internal and external scaffolding -Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
32 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - To perform internal inspection for LCS. +Check tightness of cable gland connection and other devices attached on LCS + Re-tighten on cable terminal - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
33 | 4 | 061 | MISCELLANEOUS | Check and cleaning desuperheater | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
34 | 4 | 061 | HEAT EXCHANGER | - Open, clean shell,channel,tube bundle -Visual internal inspection for shell, head and tube bundle -IRIS for tube as SEIP -Repair if require -Tightness test after repair | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
35 | 4 | 061 | HEAT EXCHANGER | - Open, clean shell,channel,tube bundle -Visual internal inspection for shell, head and tube bundle as SEIP -Retube all tube bundle -Tightness test after repair | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
36 | 4 | 061 | FILTERS/Valve | Replace new Filter '-To remove the valves to WS - To repair the valves at WS - To reinstall the valves at site | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
37 | 4 | 061 | MISCELLANEOUS | - Vendor required to do preventive, service maintenance and calibrate to bring above 08 Smart flow meterings to normal operation with reliability and accuracy. - Vendor will provide services report. The service report shall also include a professional advice on the condition of the Equipment and any recommendations that may be implemented to improve the reliability and performance of the Equipment. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
38 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
39 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
40 | 4 | 061 | Instrument equipment | DO PREVENTIVE MAINTENANCE FOR INSTRUMENT AT 061-A-502 | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
41 | 4 | 061 | Instrument equipment | DO PREVENTIVE MAINTENANCE FOR INSTRUMENT AT LOOP REACTOR | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
42 | 4 | 061 | On-Off valve | DO PREVENTIVE MAINTENANCE FOR ON/OFF VALVE Stroke test | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
43 | 4 | 061 | CONTROL VALVE | Remove and overhaul valves to do maintenance | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
44 | 4 | 061 | On-Off valve | DO PREVENTIVE MAINTENANCE FOR SHUTOFF BALL VALVE Stroke test | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
45 | 4 | 061 | Instrument equipment | DO PREVENTIVE MAINTENANCE FOR INSTRUMENT AT LOOP REACTOR | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
46 | 4 | 061 | VESSEL | -Remove tagname by cutting -Visual inspection for external shell corrosion - UTM by Inspection if any -Re-install tagname by welding | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
47 | 4 | 061 | Instrument equipment | DO PREVENTIVE MAINTENANCE FOR INSTRUMENT AT LOOP REACTOR | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
48 | 4 | 061 | On-Off valve | DO PREVENTIVE MAINTENANCE FOR ON/OFF VALVE Stroke test | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
49 | 4 | 061 | MISCELLANEOUS | Replace lube oil as PM WOs | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
50 | 4 | 061 | COMPRESSOR | Replace lube oil, run test separate lube oil pump. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
51 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
52 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
53 | 4 | 061 | MANUAL VALVE | Remove/reinstall manual valves to fix passing. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
54 | 4 | 061 | MANUAL VALVE | Remove/reinstall manual valves to fix passing. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
55 | 4 | 061 | PIPING | To open and clean suction & discharge spool of exhauted blower | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
56 | 4 | 061 | ELECTRIC MOTOR | Replace lubricant oil for bearing HV Motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
57 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
58 | 4 | 061 | ELECTRIC MOTOR | - Remove motor to WS to Replace new bearing + Replace new bearing + Inspection & repair bearing housing loosen by coating method - Perform the corrective action as per RCA for Motor vibration: Reinforce the motor foundation structure, Verify flatness of motor foof surface, Verify flatness of motor foundation struture at site - Inspection cable terminal box for motor - To perform inspection and cleaning for the ventilation fan - IR Test & measure resistance for motor - Solo run for motor - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
59 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - To perform internal inspection for LCS. +Check tightness of cable gland connection and other devices attached on LCS + Re-tighten on cable terminal - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
60 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - To perform internal inspection for LCS. +Check tightness of cable gland connection and other devices attached on LCS + Re-tighten on cable terminal - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
61 | 4 | 061 | CONTROL VALVE | Remove/reinstall control valve to fix Actuator leaking | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
62 | 4 | 061 | ELECTRIC MOTOR | - Remove old motor - IR Test & measure resistance for new motor - Install new motor & solo run - ROT support to re-coupling & alignment - MRT for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
63 | 4 | 061 | MIXER | OEM : Daega Powder OEM Engineer: No To do overhaul -Install internal and external scaffold. -Remove Coupling Guard and coupling. -Remove the motor. -Gear box inspection -Replace the lubricants. -Remove and inspect, replace Bearing, packing. -Inspect the lower shaft and blade condition. -Remove any internal and external scaffolding -Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
64 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
65 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
66 | 4 | 061 | VSD | - Replacement for end of lifetimes parts in VSD - Solo run motor - Run test motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
67 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
68 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
69 | 4 | 061 | PUMP | OEM : Flowserve OEM Engineer: Yes Do overhaul -Install external scaffold. -Instrument support to remove the sensors if any. -Remove Coupling Guard and coupling. -Disconnect and remove compressor to WS for Overhaul. -Remove and inspect, replace Bearing, Mechanical Seal. -Propeller inspection. -Lube oil replacement. -Measuring parts and final alignment. -Remove any external scaffolding. -Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
70 | 4 | 061 | PUMP | - Remove pump to workshop for inspection - Check and replace bushing -Reinstall pump and run test | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
71 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
72 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing + Inspection & repair bearing housing loosen by coating method +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - To perform inspection and cleaning for the ventilation fan - To perform inspection and cleaning for the cooling system - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
73 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing + Inspection & repair bearing housing loosen by coating method +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - To perform inspection and cleaning for the ventilation fan - To perform inspection and cleaning for the cooling system - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
74 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
75 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
76 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - Check and cleaning ventilation fan - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
77 | 4 | 061 | ELECTRIC MOTOR | - Remove motor and bring to workshop to do maintenance & replace bearing + Replace new bearing + Inspection housing bearing +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for terminal box. +Check tightness of cable gland connection and check torque on cable terminal +Visual check for inside of motor terminal box and clean as needed - To perform inspection and cleaning for the ventilation fan - To perform inspection and cleaning for the cooling system - Touch up the paint for motor - Re-install motor at site and do solo run test - Do alignment, re-connect coupling and run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
78 | 4 | 061 | ELECTRIC MOTOR | - To perform internal inspection for terminal box. +Check tightness of cable gland connection and Check torque on cable terminal +Visual Check for inside of motor terminal box and clean as needed +Measure insulation resistance (IR) of motor’s windings +Check resistance for motor’s windings, space heaters and sensors (PTC) - To perform internal inspection for LCS. +Check tightness of cable gland connection and other devices attached on LCS + Re-tighten on cable terminal - Check and cleaning ventilation fan - Run test for motor | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
79 | 4 | 061 | RELIEF VALVE | Remove/reinstall PSV valves to fix passing. - Recalibrate for PSV | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
80 | 4 | 061 | RELIEF VALVE | - To remove PSV to WS. - To inspect (NDT if required) - To replace soft part and hard part if any damage - To pop up test and attach lead seal and tag name. - To re-install at site. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
81 | 4 | 061 | Instrument equipment | DO PREVENTIVE MAINTENANCE FOR INSTRUMENT AT 061-A-502 | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
82 | 4 | 061 | Sight Glass | Check and repair Mesh of sight glass | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
83 | 4 | 061 | Instrument equipment | DO PREVENTIVE MAINTENANCE FOR INSTRUMENT AT 061-A-301 | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
84 | 4 | 061 | Instrument equipment | DO PREVENTIVE MAINTENANCE FOR INSTRUMENT AT 061-A-501 | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
85 | 4 | 061 | CONTROL VALVE | DO PREVENTIVE MAINTENANCE FOR CONTROL VALVE ( Stroke test, cable, … Not remove valve) | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
86 | 4 | 061 | On-Off valve | DO PREVENTIVE MAINTENANCE FOR SAFETY ON/OFF VALVE Stroke test | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
87 | 4 | 061 | VESSEL | To open, inspection and cleaning | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
88 | 4 | 061 | VESSEL | Isolate, Open Manhole, Replace internal mesh of hopper, Rotate hopper direction as MOC designed close manhole, deisolate | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
89 | 4 | 061 | Instrument equipment | DO PREVENTIVE MAINTENANCE FOR INSTRUMENT AT METERING FEEDER TRAIN 1 | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
90 | 4 | 061 | Instrument equipment | DO PREVENTIVE MAINTENANCE FOR INSTRUMENT AT METERING FEEDER TRAIN 2 | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
91 | 4 | 61 | Rotating equipment | OEM : JSW OEM Engineer: Yes To inspection for Performance test cutter train 1 (Build up FW Pressure & Speed curve.) | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
92 | 4 | 061 | CUTTER UNIT | Overhaul cutter due cutter moving not smoothly as RCA requirement. - Remove piping and Instruments (UWC, SLOT DISC, Inlet Hopper Etc.) - Disconnect Cutter Unit Carriage and coupling - Remove cutter unit to workshop for inspection. - Check and replace bearing,slipper ring, packing, Mechanical seal - Check Universal Joint coupling - Reinstall cutter unit, connect coupling, alignment - Build up FW Pressure & Speed curve. - Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
93 | 4 | 061 | GEARBOX | Replace new lube oil for Extruder gear box. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
94 | 4 | 061 | GEARBOX | Replace new lube oil for Extruder gear box. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
95 | 4 | 061 | MISCELLANEOUS | OEM : Zohncrane. - Remove the instruments. - Open the top cover. - Remove the piston seal and inspection and replace repair kit and reinstall. - Inspection piston rod - Install the cover - Do leak test check -Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
96 | 4 | 061 | MISCELLANEOUS | Rectify and Inspection seal pot to fix the issue difficult filling - Open the top cover. - Remove the piston seal and inspection and replace repair kit and reinstall. - Install the cover - Do leak test check -Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
97 | 4 | 061 | ROTARY FEEDER | OEM : Coperion Do overhaul - Install external scaffold. - Chain and sprocket inspection. - Gland packing replacement. - Rotor inspection. - Check/inspect clearence - Bearing inspection and replacement. - Replace oil. - Remove any external scaffolding - Housekeeping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
98 | 4 | 061 | PIPING | Replace new bolts & Nuts for the piping. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
99 | 4 | 061 | PIPING | Deplugging the piping by Cutting/welding work. Replace new piping and valve is prefered. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
100 | 4 | 061 | PIPING | - Remove spool and remove painting to do inspection for piping ebow - NDE and visual Inspection as SPIP - Re- painting and re-install after Inspection activities | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
101 | 4 | 061 | ELECTRIC MOTOR | Perform periodic IR test | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
102 | 4 | 061 | SWITCHGEAR | Replace MD21 (HMI) for MCC & check communication cable | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn
103 | 4 | 061 | PIPING | - Dismantle and cleaning TK Catalyst feeding pipeline 1/2"-TK-061-1410-D41F05-LJ. Do inspection by bore scope before and after cleaning (flange nozzle 1/2") - Scaffolding requirement.. | 1 | Thiết bị | 24/11/2025-02/12/2025 | Nhà máy Lọc hóa dầu Nghi Sơn