TECHNICAL REQUISITION FOR PIPING CLEANING SERVICE

Unit No.: Not Applicable

Unit Abbreviation.: -

Document Class: Z

| Issue Purpose |  |
| --- | --- |

| Rev | Date | Page | Description | Prepared by PTSC | Reviewed by PTSC | Approved by PTSC |
| --- | --- | --- | --- | --- | --- | --- |
| A |  | All | First Issue |  |  |  |

Contents

1.	GENERAL	3

2.	Document Control & Identification	3

3.	SCOPE OF WORK (SOW)	3

3.1. Subcontractor Responsibilities	3

3.2. Contractor (PTH) Support Scope	3

4.	TECHNICAL & QUALITY REQUIREMENTS	3

4.1. Applicable International Standards	3

4.2. CLASSIFICATION of Cleaning Methods	4

4.2.1. Water Flushing	4

4.2.2. Air Blowing	4

4.2.3. Aqua milling	4

4.2.4. Steam Blowing	4

4.2.5. Oil Flushing	5

4.2.6. Degreasing (Alkaline cleaning)	5

4.2.7. Acid Wash, Rinse & Passivate	5

4.2.8. Manual Cleaning	5

4.2.9. High Pressure Water Jet Cleaning	5

5.	Clean Build Method	6

6.	Equipment Isolation & Component Protection	6

7.	QA/QC & INSPECTION HOLD POINTS	6

7.1. Mandatory Hold Point (HP) Schedule	6

7.2. Clean-Build & Documentation	6

8.	Application cleaning	7

9.	HEALTH, SAFETY & ENVIRONMENT (HSE) REQUIREMENTS	7

9.1. Hazardous Mediums & PPE	7

9.2. Exclusion Zones (Line of Fire)	7

9.3. Environmental Compliance	7

9.4. Physical Hazard Mitigation	8

10.	DELIVERABLES & AS-BUILT DOSSIER	8

11.	Attachements	8

	Attachment-1: Summary of pipe cleaning classification for process service and special classification	8

	Attachment-2: Summary of pipe cleaning classification for utility service	8

# GENERAL

The objective of this document is to establish the stringent technical, quality, and safety requirements for the execution of internal cleaning, chemical picking, passivation, and high-velocity flushing of process piping systems. The primary mission is to achieve an absolute mechanically clean and passive internal surface for all piping networks prior to pre-commissioning and commissioning. Adherence to these requirements is mandatory to prevent flow restriction, valve malfunction, catastrophic damage to rotating equipment, and process contamination.

# Document Control & Identification

The following project-specific and international standards shall govern the work:

- S-000-1710-0100V: Pipe Cleaning Guide

- S-000-1710-0001V: Pre-commissioning and Commissioning Execution Plan

- S-000-1710-0140V: General Pre-commissioning & Commissioning Procedure for Chemical Cleaning

- S-000-1710-0160V: General Pre-commissioning Procedure for Lube Oil Flushing

- 3550-8440-SP-0027: Pre-commissioning Cleaning of Pipework and Equipment

- S-000-1140-0001V: Project Coordination Procedure

- S-000-1240-0111V: Environmental Design Basis

- S-000-1654-0920V: Waste Management Plan

- API 614 5th Edition: Lubrication, Shaft-sealing and Oil-control systems and Auxiliaries

# SCOPE OF WORK (SOW)

## Subcontractor Responsibilities

The Subcontractor shall provide a complete full package solution, including all engineering, supervision, labor, and equipment for the successful completion of the works:

- Personnel: Provision of qualified Site Supervisors, QA/QC Inspectors, dedicated HSE Officers, and certified Pump/Jetting Operators.

- Equipment & Machinery: Acid-proof chemical circulation pumps, HP water jetting units (1000 bar), temporary chemical mixing tanks, certified high-pressure flexible hoses, and automatic hose feeding devices for Aqua Milling.

- Consumables: Provision of specialized chemicals (degreasers, inhibitors, HNO_3 + HF pickling solutions/gels, neutralizing agents), demineralized (DI) water, and high-purity Nitrogen (N2) gas or equivalent chemical approved by NSRP.

- Pre-engineering: Fabrication and installation of all temporary bypass spools, acid-resistant gaskets, and certified test blinds.  Crucially, the Subcontractor must provide piping stress and thrust force calculations for all temporary loops and bypasses, specifically for HHPS (136 bar) lines.

## Contractor (PTH) Support Scope

PTH shall provide the following support services:

- Provision of heavy-duty structural scaffolding and safe work platforms designed to withstand dynamic thrust forces during high-velocity flushing and blowing.

- Supply of tie-in points for raw water and utility power at site boundaries.

- Coordination with NSRP for PTW issuance, JSA validation, and site access control.

# TECHNICAL & QUALITY REQUIREMENTS

## Applicable International Standards

All execution must strictly comply with the following governing codes:

- ASTM A380: Standard Practice for Cleaning, Descaling, and Decontaminating Stainless Steel.

- ASTM A967: Standard Specification for Chemical Passivation Treatments.

- API 527 / ASME Section VIII: Seat Tightness of Pressure Relief Valves (for safety valve calibration).

- ISO 4406 / NAS 1638: Cleanliness codes for fluid power and lube oil contamination.

## CLASSIFICATION of Cleaning Methods

### Water Flushing

- This method is widely used in pipe cleaning and is usually applied to pipes where liquid flow during normal operation. Kinetic energy generated by pumps or obtained by gravity with pre-filled water with proper volume is used to flush foreign materials from pipes or collect them in filters/strainers for removal.

- Water must be air blown out of system to avoid damage to pipe or contamination of process.

### Air Blowing

- As in the case of water flushing above, air blowing is widely used for pipe cleaning. Oil and moisture-free air is used in volumes equal to or greater than system being blown to reach a velocity to remove all debris.

### Aqua milling

- Aqua Milling is an advanced internal pipeline cleaning methodology that integrates high-pressure water jetting with automated mechanics. Its distinct technical advantage lies in its proprietary nozzle design (Aqua Mill Nozzle) and its automated drive/guidance system.

- Instead of manual hose handling (pushing and pulling) typically associated with conventional Hydro jetting, the Aqua Milling system utilizes a specialized nozzle equipped with fluid-dynamic steering vanes. Powered by high-pressure water streams (700-1,200 bar), the nozzle automatically generates two synchronized mechanical movements:

- Ultra-High Speed Axial Rotation: The nozzle spins rapidly around its own axis, acting as a highly efficient hydraulic drill.

- Self-Propelled Forward and Backward Translation: The nozzle generates its own forward thrust to advance into the pipeline and retracts uniformly, fully governed by an Automatic Feeding Device (Hose Feeder).

### Steam Blowing

- The objective of steam blowing and air blowing are basically the same, the characteristic of steam needs to be taken into consideration when used as a blowing medium. Steam Blowing is applied to the cleaning of steam pipes.

- A considerable benefit of steam-blowing is the ability to alternate the temperature to cause expansion and contraction of the pipe thus “cracking” off loose mill scales and welding slag which is then removed by blowing. This is especially beneficial on supply lines to steam driven equipment.

INDRA

25-AUG-2016

### Oil Flushing

- Oil flushing is applied to cleaning of lube oil and seal oil lines for rotating machines. Foreign materials and debris (rust, weld slag) are caught and removed by filters installed in oil flushing loop.

- Steam or Air blowing may be conducted as pre-cleaning before installation of the piping, then, lube oil flushing will be conducted after installation.

### Degreasing (Alkaline cleaning)

- Degreasing with an Alkaline solution such as Sodium Carbonate / Soda Ash (Na2CO3) results in the removal of grease and oils from the piping. This method is applied for example to prevent foaming in amine service.

### Acid Wash, Rinse & Passivate

- Acids are used to remove ionic deposits such as rust and mill scale from piping and equipment. After acid washing, the piping is rinsed and passivated to protect the metal from corrosion.

- This method will be applied for Cooling Water System but depending on passivation method selected by chemical supplier.

### Manual Cleaning

- Pipes are manually cleaned by workers inside pipes. This method is applied to the cleaning of

- large-diameter pipes (20 inches or larger), to which it appears difficult to apply other cleaning methods.

### High Pressure Water Jet Cleaning

- This method involves using high pressure water against the surface to remove surface contaminants and loose particles. A hose is inserted into the pipe with a high-pressure nozzle that rotates to clean the inside diameter of the pipe.

- High pressure water jet cleaning is applied in B400 area for steam services as alternative of steam blowing due to delay in Utility Boiler start-up that leads to delay in steam availability. The scope of water jet cleaning might be extended to the steam services in Interconnection (AG00) and Process inside if steam availability for blowing is delayed.

# Clean Build Method

The philosophy of Clean Build method is to keep the cleanliness prepared at shop fabrication stage until operation by the exhaustive cleanliness management.

This method will be applied to the piping;

- which size is too big to achieve the target cleanliness by the cleaning using kinetic energy of fluid and gas flow

- where the cleaning is difficult after installation of piping due to piping layout, configuration etc...

# Equipment Isolation & Component Protection

- Mandatory Isolation: Use spacer blinds or temporary bypass spools for Globe, Check, Control, and Pressure Safety Valves (PSVs). No chemical or jetting media shall pass through permanent instruments.

- Inline Valve Care: Ball and Gate valves remaining inline must be periodically cycled during flushing to clear trapped debris in cavities.

# Clean-Build & Documentation

- Clean Build Method: Mandatory for large bore piping ( 26") or where target cleanliness cannot be achieved by kinetic energy due to complex piping layout and configuration.

- Operational Logs: Maintenance of hourly Ca-Logs tracking pressure, temperature, and chemical concentrations is mandatory.

# Application cleaning

- Cleaning methods are classified as typical in the attached table (Attachment-1, 2) based upon industry norms and experiences. The recommended method herein may be altered at site to reflect site conditions, commissioning schedule, results of cleaning method employed, and or availability of utilities.

- Manufacturer’s instructions for cleaning must always be followed.

- Necessary record forms shall be defined and utilized for cleaning activities. Contractors will compile all necessary record sheets and handover the systems to Employer with them.

# HEALTH, SAFETY & ENVIRONMENT (HSE) REQUIREMENTS

## Hazardous Mediums & PPE

- Handling of HF and HNO3 requires visible MSDS. Personnel must wear acid-resistant full-face visors, rubber aprons, and long chemical gloves.

- Mandatory First Aid: Calcium Gluconate Gel must be present at the work site.  Work shall be suspended immediately if the gel is absent.

## Exclusion Zones (Line of Fire)

- Operation, Exclusion Zone Radius

- High-Pressure Water Jetting (HPWJ) ~15 Meters

- HHPS Steam Blowing (Free Blow / Xả tự do) ~ 70 Meters

## Environmental Compliance

- Containment: All acidic waste must be collected in dedicated tanks.

- Neutralization:  Effluent must be treated to a stable PH 6.5–8.5 before transfer to NSRP disposal facilities.

## Physical Hazard Mitigation

- Noise: Use temporary silencers for steam blowing. Ear protection is mandatory.

- Contact Burns: Barricade or insulate hot lines.

- Asphyxiation: Oxygen monitoring is mandatory before system entry; strictly follow Confined Space Entry procedures.

# DELIVERABLES & AS-BUILT DOSSIER

The Subcontractor shall submit one hardcopy and one digital copy of the final dossier including:

- Approved Method Statements and marked-up P&IDs.

- Material Certificates and MSDS for chemicals and N2 gas.

- Operational logs (Pressure, Temperature, Chemical concentrations, N2 preservation).

- Valid Calibration Certificates for all instruments and gauges.

- Formal QA/QC Inspection Reports (Videoscope logs, Chloride tests, ASTM A967 sheets).

# Attachements

# Attachment-1: Summary of pipe cleaning classification for process service and special classification

# Attachment-2: Summary of pipe cleaning classification for utility service