## Equipment List
STG 3 REPLACEMENT PROJECT EQUIMENT LIST
No | Equipment Name | Tag Name | Remark
1 | MOV | 113-HV-7341A
2 | Pressure Regulator | 113-PCV-7351
3 | Pressure Regulator | 113-PCV-7355
4 | Control Valve | 113-TV-7305
5 | Pressure Regulator | 113-TCV-7353
6 | On/Off Valve | 113-UV-7331
7 | Overhead Crane | 113-CR-003
8 | Expansion joint | 113-Y-9302B
9 | Special support for spring | 113-CH5-0051
10 | Special support for spring | 113-CH5-0034
11 | Special support for spring | 113-CH5-0035
12 | Special support for spring | 113-CH5-0036
13 | Steam trap | 00S-ST-P020
14 | Steam trap | 113-ST-0003
15 | Strainer | 113-STR-9304
16 | Strainer | 113-STR-9305A
17 | Strainer | 113-STR-9305B
18 | De-superheater | 113-ST-301-DS01
19 | Level Transmitter Displacer | 113-LT-7356
20 | Pressure Gauge | 113-PG-7320
21 | Pressure Gauge | 113-PG-7332
22 | Pressure Gauge | 113-PG-7341A
23 | Pressure Gauge | 113-PG-7341B
24 | Pressure Gauge | 113-PG-7344A
25 | Pressure Gauge | 113-PG-7345A
26 | Pressure Gauge | 113-PG-7351
27 | Pressure Gauge | 113-PG-7352
28 | Pressure Gauge | 113-PG-7353
29 | Pressure Gauge | 113-PG-7355A
30 | Pressure Gauge | 113-PG-7355B
31 | Pressure Gauge | 113-PG-7355C
32 | Pressure Gauge | 113-PG-7356A
33 | Pressure Gauge | 113-PG-7356B
34 | Pressure Gauge | 113-PG-7382
35 | Orifice Plate | 113-RO-7307
36 | Thermocouple | 113-TE-7305A
37 | Thermocouple | 113-TE-7305B
38 | Thermocouple | 113-TE-7315
39 | Temperature Gauge | 113-TG-7331
40 | Temperature Gauge | 113-TG-7332
41 | Temperature Gauge | 113-TG-7341
42 | Temperature Gauge | 113-TG-7344
43 | Temperature Gauge | 113-TG-7353
44 | Temperature Gauge | 113-TG-7354
45 | Temperature Gauge | 113-TG-7356
46 | Temperature Gauge | 113-TG-7371
47 | Temperature Transmitter | 113-TT-7305A
48 | Temperature Transmitter | 113-TT-7305B
49 | Temperature Transmitter | 113-TT-7351
50 | Sight Glass | 113-SG-7355A
51 | Sight Glass | 113-SG-7355B
52 | Pressure Relief Valve | 113-PSV-7367B
53 | Pressure Relief Valve | 113-PSV-7367D
54 | Pressure Relief Valve | 113-PSV-7314

## Vendor Print
NSRP STG3 REPLACEMENT PROJECT VENDOR PRINT UPDATING LIST - MAIN ITEMS
REV:
[8 empty] | Date: | 2025-09-12
S/N | FWBS Code | DOC.No | Document Title | REV. | Update/New/Optional | Submit Purpose | Submit Date | Approval Date | Remark
1. MANAGEMENT
1 |  |  |  | A
2. PROCESS
2
3
4
5
3. MECHANICAL
1. PIPING
Spring Support
1 |  | TBU | Load capacity
2 |  | TBU | Travel range (vertical movement, horizontal if applicable)
3 |  | TBU | Spring rate / stiffness
4 |  | TBU | Type and size of spring hanger or support
5 |  | TBU | Dimensions (height, width, installation space)
6 |  | TBU | Connection details (clamps, base plates, rods, turnbuckles, etc.)
7 |  | TBU | Orientation and installation requirements
8 |  | TBU | Spring type and quantity
9 |  | TBU | Accessories (rods, pins, plates, etc.)
10 |  | TBU | Vendor’s recommended installation procedure
11 |  | TBU | Adjustment methods for cold setting/hot setting
12 |  | TBU | Inspection and maintenance guidelines
13 |  | TBU | Test reports (load test, travel test)
14 |  | TBU | Material certificates
15 |  | TBU | Compliance certificates
16 |  | TBU | Stress Analysis Report if the spring constant or travel changes
17 |  | TBU | Piping Isometric Drawings
18 |  | TBU | 3D Model to reflect actual vendor dimensions
Special Item
1 |  | TBU | Design pressure and temperature
2 |  | TBU | Material of construction (body, internals, gasket, bolting)
3 |  | TBU | Size, rating, end connection type (flanged, welded, threaded, etc.)
4 |  | TBU | Special design parameters
5 |  | TBU | Overall dimensions and face-to-face length
6 |  | TBU | Nozzle/connection details
7 |  | TBU | Orientation requirements
8 |  | TBU | Space requirement for installation and maintenance
9 |  | TBU | List of main components and replaceable parts
10 |  | TBU | Spare parts recommendation (if any)
11 |  | TBU | Installation procedure and alignment requirements
12 |  | TBU | Operating limits and restrictions
13 |  | TBU | Maintenance and inspection guidelines
14 |  | TBU | Factory Acceptance Test (FAT) reports (if applicable)
15 |  | TBU | Pressure test / Hydrotest certificates
16 |  | TBU | Material Test Certificates
17 |  | TBU | Compliance certificates (ASME, API, EN, etc.)
18 |  | TBU | Piping Isometric Drawings (dimensions, weight, support location)
19 |  | TBU | Stress Analysis Report (especially for heavy or flexible items like expansion joints)
20 |  | TBU | Line List / Equipment List with vendor data
21 |  | TBU | 3D Model with accurate dimensions and nozzles
2. ELECTRICAL
Lighting Fixtures
1 |  | TBU | General Arrangement Drawings For Lighting Fixtures
2 |  | TBU | Name Plate Drawings For Lighting Fixtures
3 |  | TBU | Electrical Wiring Diagrams For Lighting Fixtures
4 |  | TBU | Data Sheets For Lighting Fixtures
5 |  | TBU | Test reports
6 |  | TBU | Certificate of Compliance For Lighting Fixtures
7 |  | TBU | Hazardous Classification Certifcations (IECEx, ATEX)
Electrical Cables (HV and LV)
1 |  | TBU | Vendor Data Index & Schedule For HV and LV Cables
2 |  | TBU | Specification For MV and LV Cables
3 |  | TBU | Test reports
4 |  | TBU | Certificate of Compliance For Lighting Fixtures
3. INSTRUMENTATION
MOV Valve Package
1 |  | TBU | Vendor Data Index & Schedule For Motor Operated Valves
2 |  | TBU | Engineering, Procurement, Manufacturing and Test Schedule For Motor Operated Valves
3 |  | TBU | Delivery, Handling and Packing Proposals For Motor Operated Valves
4 |  | TBU | Vendor’s Sub-Orders (Un-Priced copy) For Motor Operated Valves
5 |  | TBU | Proven Design and Manufacturing Experience List For Motor Operated Valves
6 |  | TBU | Torque Sizing Calculations For Motor Operated Valves
7 |  | TBU | General Arrangement Drawings For Motor Operated Valves
8 |  | TBU | Name Plate Drawings For Motor Operated Valves
9 |  | TBU | Electrical Wiring Diagrams For Motor Operated Valves
10 |  | TBU | Data Sheets For Motor Operated Valves
11 |  | TBU | Descriptive Literature and Catalogue Information For Motor Operated Valves
12 |  | TBU | Recommended Spare Parts For 2 Year Operation, Priced For Motor Operated Valves
13 |  | TBU | Recommended Spare parts for Start-up & Commissioning, Priced For Motor Operated Valves
14 |  | TBU | Utility Requirements – Power For Motor Operated Valves
15 |  | TBU | Loading, Transport and Unloading Details For Motor Operated Valves
16 |  | TBU | Preservation and Storage Procedure For Motor Operated Valves
17 |  | TBU | Hazardous Area Dossier For Motor Operated Valves
18 |  | TBU | Packing List For Motor Operated Valves
19 |  | TBU | Preparation for Shipment Procedure For Motor Operated Valves
20 |  | TBU | Performance and Test Procedure For Motor Operated Valves
21 |  | TBU | FAT Reports 01 For Motor Operated Valves
22 |  | TBU | Inspection and Test Plan For Motor Operated Valves
23 |  | TBU | Inspection and Test Reports For Motor Operated Valves
24 |  | TBU | Hazardous Area Certification, IP Certification For Motor Operated Valves
25 |  | TBU | Surface Preparation for Painting and Internal Coating Procedure For Motor Operated Valves
26 |  | TBU | Factory Acceptance Test Procedure and Report For Motor Operated Valves
27 |  | TBU | Certificate of Compliance For Motor Operated Valves
28 |  | TBU | Installation, Operation and Maintenance Manual (IOM) For Motor Operated Valves
29 |  | TBU | Manufacturer’s Data Book (MDB) For Motor Operated Valves
30 |  | TBU | Manufacturer’s Data Book (MDB) Index For Motor Operated Valves
Control Valves
1 |  | TBU | Vendor Data Index & Schedule For Control valves
2 |  | TBU | Engineering, Procurement, Manufacturing and Test Schedule For Control valves
3 |  | TBU | Delivery, Handling and Packing Proposals For Control valves
4 |  | TBU | Vendor’s Sub-Orders (Un-Priced copy) For Control valves
5 |  | TBU | Proven Design and Manufacturing Experience List For Control valves
6 |  | TBU | General Arrangement Drawings For Control valves
7 |  | TBU | Name Plate Drawings For Control valves
8 |  | TBU | Electrical Wiring Diagrams For Control valves
9 |  | TBU | Data Sheets For Control valves
10 |  | TBU | Descriptive Literature and Catalogue Information For Control valves
11 |  | TBU | Recommended Spare Parts For 2 Year Operation, Priced For Control valves
12 |  | TBU | Recommended Spare parts for Start-up & Commissioning, Priced For Control valves
13 |  | TBU | Utility Requirements – Power For Control valves
14 |  | TBU | Loading, Transport and Unloading Details For Control valves
15 |  | TBU | Preservation and Storage Procedure For Control valves
16 |  | TBU | Hazardous Area Dossier For Control valves
17 |  | TBU | Packing List For Control valves
18 |  | TBU | Preparation for Shipment Procedure For Control valves
19 |  | TBU | Performance and Test Procedure For Control valves
20 |  | TBU | FAT Reports For Control valves
21 |  | TBU | Inspection and Test Plan For Control valves
22 |  | TBU | Inspection and Test Reports For Control valves
23 |  | TBU | Hazardous Area Certification, IP Certification For Control valves
24 |  | TBU | Surface Preparation for Painting and Internal Coating Procedure For Control valves
25 |  | TBU | Factory Acceptance Test Procedure and Report For Control valves
26 |  | TBU | Certificate of Compliance For Control valves
27 |  | TBU | Installation, Operation and Maintenance Manual (IOM) For Control valves
28 |  | TBU | Manufacturer’s Data Book (MDB) For Control valves
29 |  | TBU | Manufacturer’s Data Book (MDB) Index For Control valves
Instrument Transmitter Devices
1 |  | TBU | Vendor Data Index & Schedule For Instrument Transmitter Devices
2 |  | TBU | Engineering, Procurement, Manufacturing and Test Schedule For Instrument Transmitter Devices
3 |  | TBU | Delivery, Handling and Packing Proposals For Instrument Transmitter Devices
4 |  | TBU | Vendor’s Sub-Orders (Un-Priced copy) For Instrument Transmitter Devices
5 |  | TBU | General Arrangement Drawings For Instrument Transmitter Devices
6 |  | TBU | Name Plate Drawings For Instrument Transmitter Devices
7 |  | TBU | Data Sheets For Instrument Transmitter Devices
8 |  | TBU | Descriptive Literature and Catalogue Information For Instrument Transmitter Devices
9 |  | TBU | Preservation and Storage Procedure For Instrument Transmitter Devices
10 |  | TBU | Packing List For Instrument Transmitter Devices
11 |  | TBU | Preparation for Shipment Procedure For Instrument Transmitter Devices
12 |  | TBU | FAT Reports For Control valves
13 |  | TBU | Inspection and Test Plan For Instrument Transmitter Devices
14 |  | TBU | Hazardous Area Certification, IP Certification For Instrument Transmitter Devices
15 |  | TBU | Factory Acceptance Test Procedure and Report For Control valves
16 |  | TBU | Certificate of Compliance For Instrument Transmitter Devices
17 |  | TBU | Installation, Operation and Maintenance Manual (IOM) For Instrument Transmitter Devices
Field Instrument device via Pressure Gauge; Temperature Gauge; Thermocouple
1 |  | TBU | Vendor Data Index & Schedule For Field Instrument
2 |  | TBU | Engineering, Procurement, Manufacturing and Test Schedule For Field Instrument
3 |  | TBU | Delivery, Handling and Packing Proposals For Field Instrument
4 |  | TBU | Name Plate Drawings For Field Instrument
5 |  | TBU | Data Sheets For Field Instrument
6 |  | TBU | Descriptive Literature and Catalogue Information For Field Instrument
7 |  | TBU | Preservation and Storage Procedure For Field Instrument
8 |  | TBU | Packing List For Field Instrument
9 |  | TBU | Preparation for Shipment Procedure For Field Instrument
10 |  | TBU | Hazardous Area Certification, IP Certification For Field Instrument
11 |  | TBU | Factory Acceptance Test Procedure and Report For Field Instrument
12 |  | TBU | Certificate of Compliance For Field Instrument
13 |  | TBU | Installation, Operation and Maintenance Manual (IOM) For Field Instrument
Pressure Relief Valve
1 |  | TBU | Vendor Data Index & Schedule For Pressure Relief Valve
2 |  | TBU | Engineering, Procurement, Manufacturing and Test Schedule For Pressure Relief Valve
3 |  | TBU | Delivery, Handling and Packing Proposals For Pressure Relief Valve
4 |  | TBU | Name Plate Drawings For Pressure Relief Valve
5 |  | TBU | Data Sheets For Pressure Relief Valve
6 |  | TBU | Descriptive Literature and Catalogue Information For Pressure Relief Valve
7 |  | TBU | Preservation and Storage Procedure For Pressure Relief Valve
8 |  | TBU | Packing List For Pressure Relief Valve
9 |  | TBU | Preparation for Shipment Procedure For Pressure Relief Valve
10 |  | TBU | Hazardous Area Certification, IP Certification For Pressure Relief Valve
11 |  | TBU | Factory Acceptance Test Procedure and Report For Pressure Relief Valve
12 |  | TBU | Pressure test / Hydrotest certificates
13 |  | TBU | Material Test Certificates
14 |  | TBU | Compliance certificates (ASME, API, EN, etc.)
15 |  | TBU | Certificate of Compliance For Pressure Relief Valve
16 |  | TBU | Installation, Operation and Maintenance Manual (IOM) For Pressure Relief Valve
4. MECHANICAL
Overhead Crane
1 |  | TBU | Vendor Data Index & Schedule For Ovehead Crane
2 |  | TBU | Engineering, Procurement, Manufacturing and Test Schedule For Ovehead Crane
3 |  | TBU | Delivery, Handling and Packing Proposals For Ovehead Crane
4 |  | TBU | Vendor’s Sub-Orders (Un-Priced copy) For Ovehead Crane
5 |  | TBU | General Arrangement Drawings For Ovehead Crane
6 |  | TBU | Name Plate Drawings For Ovehead Crane
7 |  | TBU | Data Sheets For Ovehead Crane
8 |  | TBU | Descriptive Literature and Catalogue Information For Ovehead Crane
9 |  | TBU | Recommended Spare Parts For 2 Year Operation, Priced For Ovehead Crane
10 |  | TBU | Recommended Spare parts for Start-up & Commissioning, Priced For Ovehead Crane
11 |  | TBU | Utility Requirements – Power For Ovehead Crane
12 |  | TBU | Packing List For Ovehead Crane
13 |  | TBU | Preparation for Shipment Procedure For Ovehead Crane
14 |  | TBU | Performance and Test Procedure For Ovehead Crane
15 |  | TBU | FAT Report For Ovehead Crane
16 |  | TBU | Inspection and Test Plan For Overhead Crane
17 |  | TBU | Inspection and Test Reports For Ovehead Crane
18 |  | TBU | Wire Rope Hoist Diagram
19 |  | TBU | Surface Preparation for Painting and Internal Coating Procedure For Ovehead Crane
20 |  | TBU | Terminal box and terminal drawings for instruments and electrical equipment (incl. power / control schematics, single line diagrams, protective devices and characteristics curves)
21 |  | TBU | Installation, Operation and Maintenance Manual (IOM) For Ovehead Crane
22 |  | TBU | Manufacturer’s Data Book (MDB) For Ovehead Crane
23 |  | TBU | Manufacturer’s Data Book (MDB) Index For Ovehead Crane
5. STEAM TURBINE AND GENERATOR
1 |  | VS2158-412-A-004 | General Arrangement for Steam Turbine Generator Package
2 |  | VS2158-412-A-007 | Foundation Drawing for Steam Turbine Generator
3 |  | VS2158-412-A-999 | Vendor Document List
4 |  | VS2158-412-A-018 | Steam Turbine Expected Performance
5 |  | VS2158-412-A-031 | Arrangement of Instrument & Tapping point
6 |  | VS2158-412-A-058 | Equipment List
7 |  | VS2158-412-A-021 | Earth Arrangement Drawing
8 |  | VS2158-412-A-618 | Rust Prevent Procedure for Steam Turbine
9 |  | VS2158-412-A-035 | Piping Arrangement Drawing
10 |  | VS2158-412-A-047 | Piping Support Drawing at Site
11 |  | VS2158-412-A-060 | HP/LP Steam Blow Tool
12 |  | VS2158-412-A-064 | Export Packing Style Drawing
13 |  | VS2158-412-A-750 | Lubricant List
14 |  | VS2158-412-A-077 | Steam Turbine Outline Drawing
15 |  | VS2158-412-A-080 | Steam Turbine Cross Sectional Drawing
16 |  | VS2158-412-A-213 | P & I Diagram (Steam Turbine)
17 |  | VS2158-412-A-218 | P & I Diagram (Lube Oil System)
18 |  | VS2158-412-A-223 | P & I Diagram (Lube Oil Unit)
19 |  | VS2158-412-A-228 | P & I Diagram (Control Oil System)
20 |  | VS2158-412-A-233 | P & I Diagram (Control Oil Unit)
21 |  | VS2158-412-A-238 | P & I Diagram (Machine Monitoring Diagram)
22 |  | VS2158-412-A-248 | P & I Diagram (Inlet & Extraction Steam Line)
23 |  | VS2158-412-A-099 | Control Oil Unit Outline Drawing
24 |  | VS2158-412-A-149 | Lube Oil Unit Outline Drawing
25 |  | VS2158-412-A-640 | Inspection and Test Item List
26 |  | VS2158-412-A-614 | Inspection and Test Procedure for Steam Turbine
27 |  | VS2158-412-A-059 | Name Plate for Steam Turbine
28 |  | VS2158-412-A-074 | Valve List for Steam Turbine
29 |  | VS2158-412-A-121 | Technical Specification for Electrical Equipment
30 |  | VS2158-412-A-517 | Junction Box (For ST Unit)
31 |  | VS2158-412-A-547 | Field Instrument Label
32 |  | VS2158-412-A-613 | WPS & PQR for Steam Turbine
33 |  | VS2158-412-A-635 | Material Traceability Procedure for Steam Turbine
34 |  | VS2158-412-A-636 | Welder Qualification Record and Welder List for Steam Turbine
35 |  | VS2158-412-A-637 | Heat Treatment Procedure (Including PWHT) for Steam Turbine
36 |  | VS2158-412-A-653 | Foundation Embedded Material Layout Drawing
37 |  | VS2158-412-A-656 | Inspection Record for Embedded Material Location
38 |  | VS2158-412-A-659 | Inspection and Test Item List for Generator (for 2P)
39 |  | VS2158-412-A-661 | Repair Welding Procedure for Steam Turbine Casing
40 |  | VS2158-412-A-041 | Isometric Drawing for Lube Oil piping including Sight Glass
41 |  | VS2158-412-A-044 | Isometric Drawing for Control Oil piping
42 |  | VS2158-412-A-751 | Special Tool List
43 |  | VS2158-412-A-752 | Initial Spare Part List
44 |  | VS2158-412-A-085 | Turbine Exhaust Spray Valve
45 |  | VS2158-412-A-086 | Check Valve (Power Assisted) for Extraction Steam Line
46 |  | VS2158-412-A-088 | Expansion Joint for Steam Turbine Exhaust
47 |  | VS2158-412-A-091 | Seal steam Control Valve
48 |  | VS2158-412-A-095 | MSV Drain Valve / Casing Drain Valve
49 |  | VS2158-412-A-100 | Control Oil Unit Specification
50 |  | VS2158-412-A-101 | Noise Enclosure Outline Drawing
51 |  | VS2158-412-A-106 | Noise Enclosure Drawing
52 |  | VS2158-412-A-152 | Lube Oil Unit Specification
53 |  | VS2158-412-A-167 | Flame Arrester for LO Unit
54 |  | VS2158-412-A-110 | Generator Outline Drawing
55 |  | VS2158-412-A-118 | Performance Curve for Generator
56 |  | VS2158-412-A-646 | Test & Inspection Procedure of Generator
57 |  | VS2158-412-A-507 | Vibration Sensor Drawing for Steam Turbine
58 |  | VS2158-412-A-508 | Temperature Detector for Steam Turbine Bearing
59 |  | VS2158-412-A-511 | Speed Sensor
60 |  | VS2158-412-A-512 | Pressure Gauge
61 |  | VS2158-412-A-513 | Temperature Sensor
62 |  | VS2158-412-A-514 | Temperature Gauge
63 |  | VS2158-412-A-170 | Solenoid Valve Manifold Assembly Drawing
64 |  | VS2158-412-A-539 | Vibration Sensor Drawing for Generator
65 |  | VS2158-412-A-543 | Instrument List
66 |  | VS2158-412-A-645 | WPS & PQR for Generator
67 |  | VS2158-412-A-102 | Main Stop Valve Actuator
68 |  | VS2158-412-A-103 | Governor Valve Actuator
69 |  | VS2158-412-A-104 | Extraction Control Valve Actuator
70 |  | VS2158-412-A-128 | Turning Device
71 |  | VS2158-412-A-506 | Pressure Transmitter
72 |  | VS2158-412-A-527 | Turbine Control Panel
73 |  | VS2158-412-A-545 | Temperature Transmitter
74 |  | VS2158-412-A-522 | Main Sequence Block Diagram
75 |  | VS2158-412-A-546 | LVDT
76 |  | T-STG6/PTSC-0002 | Technical Memorandum for Turbine Casing Bolt Material Upgrade
77 |  | T-STG6/PTSC-0004 | Technical Memorandum Regarding Change of Solenoid Valve Manufacturer (from Atos to Kawasaki manufacture)
78 |  | T-STG6/PTSC-0005 | Technical Memorandum for replacement of Servo Controller (Servo Controller will be changed from MOOG to Mitsubishi)
79 |  | T-STG6/PTSC-0006 | Technical Memorandum on the Reduction of Turning Speed (from original 20 rpm to 18.1 rpm)
80 |  | T-STG6/PTSC-0007 | Technical Memorandum on Changing the Hydrostatic Test pressure of Steam Turbine Casing
81 |  | T-STG6/PTSC-0008 | Technical Memorandum for Replacing Stud-Type Diodes of Brushless Exciter
82 |  | VS2158-412-A-612 | Quality Plan
83 |  | VS2158-412-A-625 | Site Performance Test Procedure
84 |  | VS2158-412-A-804 | Installation Manual
85 |  | VS2158-412-A-801 | Operation and Maintenance Manual (Revised section only)
86 |  | VS2158-412-A-601 | Commissioning Test Procedure for Electrical
87 |  | VS2158-412-A-609 | Commissioning Test Procedure for Instrument
88 |  | VS2158-412-A-503 | Instrument List for Site Commissioning Test (Instrument &
89 |  | VS2158-412-A-605 | Commissioning Test Procedure for Mechanical
90 |  | VS2158-412-A-500 | Instrument and Consumable List for Site Commissioning Test (Mechanical)
91 |  | VS2158-412-A-900 | Index of Manufacturing Data Report (MDR)
92 |  | VS2158-412-A-903 | Manufacturing Data Report (MDR)
93 |  | VS2158-412-A-673 | Commissioning Test Report (for Mechanical)
94 |  | VS2158-412-A-678 | Commissioning Test Report (for Instrument)
95 |  | VS2158-412-A-683 | Commissioning Test Report (for Electrical)
96 |  | VS2158-412-A-634 | NDE Operator List for Steam Turbine
Note: This is the preliminary Vendor Print for the main items and can be updated upon receipt of vendor information.

## EMDR
NSRP STG3 REPLACEMENT PROJECT MASTER DELIVERABLE REGISTER LIST (MDRL)
[8 empty] | REV: | C
[8 empty] | Date: | 2025-09-12
S/N | FWBS Code | DOC.No | Document Title | REV. | Update/New/Optional | Submit Purpose | Submit Date | Approval Date | Remark
1. MANAGEMENT
1 | 1136 | S-113-1136-0001PH | MASTER DELIVERABLE REGISTER LIST (MDRL) | A
2. PROCESS
2 | 1223 | D-113-1223-0401S | PFD - UNIT 113 - STEAM TURBINE GENERATORS
3 | 1223 | D-113-1223-0403S | PFD - UNIT 113 - H & MB
4 | 1223 | D-113-1223-0901S | MSD - UNIT 113 - STEAM TURBINE GENERATORS
5 | 1223 | S-113-1223-0501S | UTILITY SUMMARY FOR STEAM TURBINE GENERATORS
6 | 1223 | S-113-1223-0502S | RELIEF AND BLOWDOWN SUMMARY
7 | 1223 | S-113-1223-0801S | CAUSE AND EFFECT DIAGRAM
8 | 1223 | S-113-1223-0803S | STATIC ALARM SUPPRESSION FOR UNIT 113
9 | 1223 | S-113-1223-0804S | DYNAMIC ALARM SUPPRESSION FOR UNIT 113
10 | 1225 | D-113-1225-0001S | P&ID - UNIT 113 - STEAM TURBINE GENERATOR PACKAGE
11 | 1225 | D-113-1225-2002S | P&ID - UNIT 113 - PUMP SEAL AND COOLING PLAN
12 | 1225 | D-113-1225-2003S | P&ID - UNIT 113 - MOTOR CONTROL DETAILS
13 | 1228 | S-113-1228-0001S | LINE LIST FOR STEAM TURBINE GENERATORS
14 | 1256 | S-113-1256-0001PH | HAZOP STUDY REPORT FOR STG6
15 | 1257 | S-113-1257-0002PH | LOPA/SIL CLASSIFICATION REPORT
16 | 1256 | S-113-1256-1002PH | HAZOP ACTION CLOSE-OUT REPORT FOR STG6
17 | 1370 | S-113-1370-5001PH | SIL VERIFICATION REPORT
3. MECHANICAL
18 |  | T-STG6/PTSC-0003 | TECHNICAL MEMORANDUM FOR THE REPLACEMENT OF OVERHEAD CRANE MODEL
19 | 135A | S-113-135A-0001PH | MECHANICAL DATASHEET FOR OVERHEAD CRANE PACKAGE (FOR STG6) | [6 empty] | x
4. PIPING
20 | 3160 | VPH3160-003-A-800 | PIPING ASSESSMENT REPORT
21 | 1362 | S-113-1362-0002PH | MECHANICAL TIE-IN LIST FOR PIPING SYSTEMS OF STEAM TURBINE GENERATOR PACKAGE (113-A-006)
22 | 1140 | T-113-1140-0001PH | 3D MODEL REVIEW CLOSE-OUT REPORT
23 | 1225 | D-B40-1225-0013S | UNIT PLOT PLAN STEAM & POWER AREA UNIT 110/111/112/113 (3/4)
24 | 1362 | D-B40-1362-1019S | PIPING GENERAL ARRANGEMENT DRAWING FOR STEAM TURBINE GENERATOR (113-A-006) (1/2)
25 | 1362 | D-B40-1362-1020S | PIPING GENERAL ARRANGEMENT DRAWING FOR STEAM TURBINE GENERATOR (113-A-006) (2/2)
26 | 1360 | C-110-1360-0001PH | PIPE STRESS ANALYSIS REPORT FOR HOT TAPPING SERVICE
27 | 1362 | D-113-1362-0001PH | HOT TAPPING ISOMETRIC
5. ELECTRICAL
28 | 3181 | VPH3181-003-A-800 | ELECTRICAL INVESTIGATION ASSESSMENT REPORT
29 | 1380 | D-000-1380-0200V | OVERALL KEY SINGLE LINE DIAGRAM
30 | 1381 | D-M02-1381-0001S | SINGLE LINE DIAGRAM FOR SUBSTATION SS-M02
31 | 1382 | D-110-1382-0009S | POWER LAYOUT STEAM & POWER UNIT 110/111/112/113 (8 OF 21)
32 | 1382 | D-110-1382-0020S | POWER LAYOUT STEAM & POWER UNIT 110/111/112/113 (19 OF 21)
33 | 1382 | D-110-1382-0041S | OVERALL BREAKDOWN CABLE LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
34 | 1382 | D-110-1382-0042S | CABLE LAYOUT STEAM & POWER UNIT 110/111/112/113 (UPDATING FOR STG6)
35 |  | T-STG6/PTSC-0001 | TECHNICAL MEMORANDUM FOR REPLACEMENT OF LED LIGHTING FIXTURES
36 | 1383 | D-110-1383-0039S | LIGHTING & SMALL POWER LAYOUTS STEAM & POWER AREA UNIT 110/111/112/113 (39 OF 102)
37 | 1383 | D-110-1383-0040S | LIGHTING & SMALL POWER LAYOUTS STEAM & POWER AREA UNIT 110/111/112/113 (40 OF 102)
38 | 1383 | D-110-1383-0098S | LIGHTING & SMALL POWER LAYOUTS STEAM & POWER AREA UNIT 110/111/112/113 (98 OF 102)
39 | 1383 | D-110-1383-1001S | OUTDOOR DISTRIBUTION BOARD SCHEDULE (UPDATING FOR STG6)
40 | 1383 | D-110-1383-0402S | LIGHTING & SMALL POWER BLOCK DIAGRAM STEAM & POWER AREA UNIT 110/111/112/113 ( 2 OF 2)
41 | 1383 | D-110-1383-0408S | LIGHTING & SMALL POWER BLOCK DIAGRAM STEAM & POWER AREA UNIT 110/111/112/113
42 | 1383 | D-110-1383-0033S | LIGHTING & SMALL POWER LAYOUTS STEAM & POWER AREA UNIT 110/111/112/113 (33 OF 102)
43 | 1383 | D-110-1383-0411S | LIGHTING & SMALL POWER BLOCK DIAGRAM STEAM & POWER AREA UNIT 110/111/112/113 ( 1 OF 2)
44 | 1384 | D-110-1384-0009S | EARTHING & LIGHTNING LAYOUT STEAM & POWER UNIT UNIT 110/111/112/113 (8 OF 22)
45 | 1382 | D-M02-1382-0101S | ELECTRICAL CABLE SCHEDULE FOR SS-M02
46 | 1383 | C-110-1383-0001PH | LIGHTING ILLUMINATION CALCULATION FOR STG6
47 | 1382 | D-M02-1382-0201S | CONNECTION LIST - SUBSTATION SS-M02
6. INSTRUMENTATION
48 | 3179 | VPH3179-006-A-800 | INSTRUMENT INVESTIGATION ASSESSMENT REPORT
49 | 1378 | D-113-1378-0401S | INSTRUMENT IMPLUSE LINE HOOK-UP (UNIT - 113)
50 | 1378 | D-113-1378-0501S | INSTRUMENT AIR LINE HOOK-UP (UNIT - 113)
51 | 1378 | D-113-1378-0701S | INSTRUMENT WIRING CONNECTION LIST & DETAIL (UNIT 113)
52 | 1370 | S-113-1370-1004S | CABLE BLOCK DIAGRAM (UNIT 113)
53 | 1374 | S-113-1374-0302PH | DATA SHEET FOR PRESSURE REGULATOR VALVE | [6 empty] | X
55 | 1360 | S-113-1360-0301S | DATA SHEET FOR MOTOR OPERATION VALVE (GATE) | [6 empty] | X
54 |  | T-STG6/PTSC-0009 | TECHNICAL MEMORANDUM FOR MOTOR OPERATED VALVE UPGRADE | [6 empty] | x
56 |  | T-STG6/PTSC-0010 | TECHNICAL MEMORANDUM FOR PRESSURE REGULATOR VALVE UPGRADE | [6 empty] | x
7. CIVIL & STRUCTURE
57 | 3111 | VPH3111-003-A-800 | CIVIL AND STRUCTURAL ASSESSMENT REPORT | X
58 | 133A | D-B40-133A-4206S | STEAM TURBINE GENERATOR SHELTER-3 113-A-006 FOUNDATION DETAILS-2 | 9
59 | 133A | D-B40-133A-4207S | STEAM TURBINE GENERATOR SHELTER-3 113-A-006 FOUNDATION DETAILS-3 | 2
60 | 133A | D-B40-133A-4208S | STEAM TURBINE GENERATOR SHELTER-3 113-A-006 FOUNDATION DETAILS-4 | 2
61 | 133A | C-B40-133A-4201S | STRUCTURAL CALCULATION FOR FOUNDATION OF B4SH007 STEAM TURBINE GENERATOR
62 | 133A | C-B40-133A-4301S | STRUCTURAL CALCULATION FOR B4SH004 STEAM TURBINE GENERATOR SHELTER-STG6
63 | 133A | D-B40-133A-4104S | STEAM TURBINE GENERATOR SHELTER-3 ELEVATIONS-2
64 | 133A | D-B40-133A-4205S | STEAM TURBINE GENERATOR SHELTER-3 113-A-006 FOUNDATION DETAILS-1
65 | 133A | D-B40-133A-4303S | STEAM TURBINE GENERATOR SHELTER-3 CRANE GIRDER & ROOF FRAMING PLAN
66 | 133A | D-B40-133A-4304S | STEAM TURBINE GENERATOR SHELTER-3 FRAMING ELEVATIONS-1
67 | 133A | D-B40-133A-4305S | STEAM TURBINE GENERATOR SHELTER-3 FRAMING ELEVATIONS-2

## CMDR.B (hidden)
NSRP STG3 REPLACEMENT PROJECT CONSTRUCTION MASTER DELIVERABLE REGISTER LIST (CMDRL)
[8 empty] | REV: | B
[8 empty] | Date: | 2025-08-04
S/N | FWBS Code | DOC.No | Document Title | REV. | Update/New/Optional | Submit Purpose | Submit Date | Approval Date | Remark
1 | 1133 | S-113-1133-0001PH | DETAILED PROJECT SCHEDULE |  | New
2 | 1120 | S-000-1120-0001PH | PROJECT ORGANIZATION CHART
3 | 1136 | S-113-1136-0002PH | PROJECT DOCUMENT CONTROL PROCEDURE |  | New
4 | 1139 | S-113-1139-0001PH | QUALITY MANAGEMNENT PLAN |  | New
5 | 1133 | S-113-1133-0002PH | PROGRESS MEASUREMENT PROCEDURE
6 | 1140 | S-113-1140-0081PH | TECHNICAL MEMORANDUM AND EMPLOYER ADVICE NOTICE PROCEDURE
7 | 1242 | S-113-1242-0001PH | HSSE EXECUTION MANAGEMENT PLAN
8 | 1133 | S-113-1133-0003PH | PROJECT REPORTING PROCEDURE
9 | 217Z | RPH217Z-001 | REQUISITION FOR INSTRUMENT DEVICE AND CABLE INVESTIGATION
10 | 212Z | RPH212Z-001 | REQUISITION FOR CIVIL AND STRUCTURE INVESTIGATION
11 | 216Z | RPH216Z-001 | REQUISITION FOR PIPING INVESTIGATION
12 | 218Z | RPH218Z-001 | REQUISITION FOR ELECTRICAL INVESTIGATION
13 | 216Z | QPH216Z-001 | TECHNICAL BID EVALUATION FOR PIPING INVESTIGATION
14 | 217Z | QPH217Z-001 | TECHNICAL BID EVALUATION FOR INSTRUMENT INVESTIGATION
15 | 218Z | QPH218Z-001 | TECHNICAL BID EVALUATION FOR ELECTRICAL INVESTIGATION
16 | 212Z | QPH212Z-001 | TECHNICAL BID EVALUATION FOR CIVIL AND STRUCTURE INVESTIGATION
17 | 3179 | VPH3179-006-A-100 | INSTRUMENT ASSESSMENT METHODOLOGY
18 | 3160 | VPH3160-003-A-100 | PIPING ASSESSMENT METHODOLOGY
19 | 3111 | VPH3111-003-A-100 | CIVIL AND STRUCTURE ASSESSMENT METHODOLOGY
20 | 3181 | VPH3181-003-A-100 | ELECTRICAL ASSESSMENT METHODOLOGY
21 | 1140 | S-113-1140-0001PH | TITLE BLOCK REQUIREMENTS FOR TECHNICAL DOCUMENTS AND DRAWINGS
22 | 1173 | S-113-1173-1001PH | MONTHLY PROGRESS REPORT
23 | 1139 | S-113-1139-0002PH | PROJECT QUALITY AUDIT PROCEDURE
24 | 1135 | S-113-1135-0002PH | HANDING OVER MATERIAL AND SITE CONDITION STATUS PLAN
25 | 1135 | S-113-1135-0003PH | OVERALL DISMANTLING PROCEDURE FOR INVESTIGATION AND DEMOLITION WORK
26 | 113Z | S-113-113Z-0001PH | PROJECT EXECUTION PLAN
27 | 1162 | S-113-1162-0001PH | WELDING CONTROL PROCEDURE
28 | 217Z | S-113-217Z-001PH | MATERIAL APPROVAL REQUEST FOR INSTRUMENT CABLE
29 | 216A | S-113-216A-001PH | MATERIAL APPROVAL REQUEST FOR PIPING MATERIAL (PIPE, FITTING, BOLT, GASKET, MANUAL VALVE)
30 | 218Z | S-113-218Z-001PH | MATERIAL APPROVAL REQUEST FOR POWER AND CONTROL CABLE
31 | 1162 | S-113-1162-0003PH | WELDING REPAIR PROCEDURE
32 | 1162 | S-113-1162-0004PH | GOLDEN WELD PROCEDURE
33 | 1162 | S-113-1162-0002PH | WELDING CONSUMABLE HANDLING AND STORE CONTROL PROCEDURE
34 | 1360 | S-113-1360-0014PH | SPECIFICATION FOR PIPING MATERIAL SUBSTITUTION AT SITE |  | New
35 | 1162 | S-113-1162-0012PH | FERRITE TESTING PROCEDURE |  | New
36 | 1162 | S-113-1162-0014PH | HARDNESS TEST PROCEDURE |  | New
37 | 1162 | S-113-1162-0022PH | LIQUID PENETRANT TESTING PROCEDURE |  | New
38 | 1162 | S-113-1162-0023PH | MAGNETIC PARTICLE TESTING PROCEDURE |  | New
39 | 1162 | S-113-1162-0005PH | NON-DESTRUCTIVE EXAMINATION PROCEDURE |  | New
40 | 1162 | S-113-1162-0006PH | POSITIVE MATERIAL IDENTIFICATION PROCEDURE |  | New
41 | 1162 | S-113-1162-0007PH | PWHT PROCUDURE |  | New
42 | 1162 | S-113-1162-0008PH | RADIOGRAPHIC TESTING PROCEDURE |  | New
43 | 1162 | S-113-1162-0009PH | ULTRASONIC TESTING PROCEDURE |  | New
44 | 1162 | S-113-1162-0010PH | WELDER PERFORMANCE QUALIFICATION |  | New
45 | 1162 | S-113-1162-0013PH | WELDING PROCEDURE SPECIFICATION |  | New
46 | 1162 | S-113-1162-0015PH | PAINTING PROCEDURE |  | New
47 | 1162 | S-113-1162-0016PH | INSULATION PROCEDURE |  | New
48 | 1162 | S-113-1162-0017PH | HYDRO AND LEAK TEST CONTROL PROCEDURE |  | New
49 | 1162 | S-113-1162-0018PH | NON-CONFORMANCE PROCEDURE |  | New
50 | 1162 | S-113-1162-0019PH | EQUIPMENT AND INSTRUMENT CALIBRATION CONTROL PROCEDURE |  | New
51 | 1162 | S-113-1162-0020PH | PROCUREMENT PROCEDURE |  | New
52 | 1162 | S-113-1162-0021PH | OVERHAUL PROCEDURES FOR CONDENSER/PUMP MOTOR/INSTRUMENT.
53 | 1635 | S-113-1635-0001PH | MATERIAL CONTROL PROCEDURE |  | New
54 | 1635 | S-113-1635-0002PH | MATERIAL IDENTIFICATION AND TRACEABILITY PROCEDURE |  | New
55 | 1671 | S-113-1671-0001PH | INSPECTION AND TEST PLAN FOR CONCRETE WORK |  | New
56 | 1671 | S-113-1671-0002PH | INSPECTION AND TEST PLAN FOR SITE PREPARATION AND EARTH WORK |  | New
57 | 1671 | S-113-1671-0003PH | INSPECTION AND TEST PLAN FOR PAVING WORK |  | New
58 | 1673 | S-113-1673-0001PH | INSPECTION AND TEST PLAN FOR STEEL STRUCTURE ERECTION |  | New
59 | 1675 | S-113-1675-0001PH | INSPECTION AND TEST PLAN FOR STATIC EQUIPMENT INSTALLATION |  | New
60 | 1675 | S-113-1675-0002PH | INSPECTION AND TEST PLAN FOR INSTALLATION OF ROTARY MACHINERY |  | New
61 | 1676 | S-113-1676-0001PH | INSPECTION AND TEST PLAN FOR PIPING WORK(AG/UG) |  | New
62 | 1676 | S-113-1676-0002PH | INSPECTION AND TEST PLAN FOR PIPE WELDING REPAIRING WORK |  | New
63 | 1676 | S-113-1676-0003PH | INSPECTION AND TEST PLAN FOR GOLDEN WELD |  | New
64 | 1677 | S-113-1677-0001PH | INSPECTION AND TEST PLAN FOR INSTALLATION OF INSTRUMENT CONSOLE, CABINET, PANEL & JUNCTION BOX |  | New
65 | 1677 | S-113-1677-0002PH | INSPECTION AND TEST PLAN FOR INSTALLATION OF INSTRUMENT CABLE |  | New
66 | 1677 | S-113-1677-0003PH | INSPECTION AND TEST PLAN FOR INSTALLATION OF INSTRUMENT CABLE TRAYS/ CONDUIT/ WAY |  | New
67 | 1677 | S-113-1677-0004PH | INSPECTION AND TEST PLAN FOR INSTRUMENT INSTALLATION |  | New
68 | 1677 | S-113-1677-0005PH | INSPECTION AND TEST PLAN FOR INSTRUMENT PRESSURE LEAK TEST FOR PRESSURE LEAD LINE, INSTRUMENT AIR LINE AND SAMPLING SYSTEM LINE |  | New
69 | 1677 | S-113-1677-0006PH | INSPECTION AND TEST PLAN FOR INSTRUMENT LOOP TEST |  | New
70 | 1677 | S-113-1677-0007PH | INSPECTION AND TEST PLAN FOR MOTOR OPERATED VALVE STROKE TEST |  | New
71 | 1677 | S-113-1677-0008PH | ITP FOR INSTRUMENT FUNCTION TEST
72 | 1678 | S-113-1678-0001PH | INSPECTION AND TEST PLAN FOR INSTALLATION, JOINTING, TERMINATION AND TESTING OF ELECTRICAL CABLES |  | New
73 | 1678 | S-113-1678-0002PH | INSPECTION AND TEST PLAN FOR INSTALLATION OF CABLE TRAYS |  | New
74 | 1678 | S-113-1678-0003PH | INSPECTION AND TEST PLAN FOR GROUNDING AND LIGHTNING PROTECTION SYSTEM |  | New
75 | 1678 | S-113-1678-0004PH | INSPECTION AND TEST PLAN FOR LIGHTING AND SMALL POWER SYSTEM |  | New
76 | 1678 | S-113-1678-0005PH | INSPECTION AND TEST PLAN FOR TESTING OF ELECTRIC MOTORS |  | New
77 | 1678 | S-113-1678-0006PH | INSPECTION AND TEST PLAN FOR FIELD ELECTRICAL EQUIPMENT (LCS, POWER JB AND ELECTRICAL HEATER) |  | New
78 | 1678 | S-113-1678-0007PH | INSPECTION AND TEST PLAN FOR ELECTRICAL / INSTRUMENTATION MATERIAL |  | New
79 | 1679 | S-113-1679-0001PH | INSPECTION AND TEST PLAN FOR INSULATION WORK |  | New
80 | 167A | S-113-167A-0001PH | INSPECTION AND TEST PLAN FOR PAINTING WORK |  | New
81 | 167B | S-113-167B-0001PH | INSPECTION AND TEST PLAN FOR FIRE PROOFING |  | New
82 | 1713 | S-113-1713-0001PH | GENERAL PRE-COMMISSIONING PROCEDURE FOR WATER FLUSHING |  | New
83 | 1713 | S-113-1713-0002PH | GENERAL PRE-COMMISSIONING PROCEDURE FOR STEAM BLOWING |  | New
84 | 1713 | S-113-1713-0003PH | GENERAL PRE-COMMISSIONING PROCEDURE FOR AIR BLOWING |  | New
85 | 1713 | S-113-1713-0004PH | GENERAL PRE-COMMISSIONING & COMMISSIONING PROCEDURE FOR CHEMICAL CLEANING |  | New
86 | 1713 | S-113-1713-0005PH | GENERAL PRE-COMMISSIONING PROCEDURE FOR LUBE OIL FLUSHING |  | New
87 | 1713 | S-113-1713-0006PH | GENERAL PRE-COMMISSIONING & COMMISSIONING PROCEDURE FOR TIGHTNESS TEST |  | New
88 | 1713 | S-113-1713-0010PH | PRE-COMMISSIONING PROCEDURE FOR AQUA MILLING. |  | New
89 | 2177 | RPH2177-201 | TECHNICAL REQUISITION FOR MOV, HV |  | New
90 | 2155 | RPH2155-504 | TECHNICAL REQUISITION FOR OVERHEAD CRANE |  | New
91 | 218Z | QPH218Z-002 | TECHNICAL BID EVALUATION FOR OVERHEAD CRANE
92 | 2174 | QPH2174-001 | TECHNICAL BID EVALUATION FOR MOV, HV
93 | 1713 | S-113-1713-0008PH | INSPECTION AND TEST PROCEDURE -OVERHEAD CRANE |  | New
94 | 2162 | S-113-2162-001PH | MAR OF STEAM TRAP, STRAINER MATERIAL |  | New
95 | 217Z | S-113-217Z-002PH | MAR OF LCS AND JUNCTION BOX |  | New
96 | 217Z | S-113-217Z-008PH | MAR OF CABLE TRAY, GLAND, CONDUIT, TUBING |  | New
97 | 2173 | S-113-2173-001PH | MAR OF GAUGE, TRANSMITTER, SWITCH |  | New
98 | 2132 | S-113-2132-001PH | MAR OF STEEL STRUCTURE MATERIAL (BEAM, COLUMN, STAIR, LADDER, ANCHOR BOLT…) |  | New
99 | 3123 | S-113-3123-001PH | MAR OF EMBEDED PLATE, REINFORCEMENT STEEL BAR, BOLT AND NUT |  | New
100 | 3132 | S-113-3132-001PH | MAR OF FIRE PROOFING MATERIAL |  | New
101 | 3191 | S-113-3191-001PH | MAR OF INSULATION MATERIAL |  | New
102 | 3123 | S-113-3123-002PH | MAR OF CIVIL MATERIAL (MOTAR, SAND, SEALANT, CEMENT, FRESH CONCRETE) |  | New
103 | 3123 | S-113-3123-003PH | MAR OF NON-SHRINK GROUTING/ SIKADUR |  | New
104 | 31A2 | S-113-31A2-001PH | MAR OF PAINTING MATERIAL |  | New
105 | 3132 | S-113-3132-002PH | MAR OF METAL SHEET (ROOF AND WALL), FLASHING, GUTTER, DOWNSPOUT, GRATING |  | New
106 | 216Z | S-113-216Z-001PH | MAR FOR WELDING ROD
107 |  | ME-NA1 | TRD FOR OVERHEAD CRANE PACKAGE (UPDATING FOR STG6)
108 | 2164 | S-113-2164-001PH | MAR FOR SPECIAL SUPPORTS

## EMDR.UN-CHANGE
NSRP STG3 REPLACEMENT PROJECT ENGINEERING DOCUMENT FOR REFERNCE
REV:
Date:
S/N | FWBS Code | DOC.No | Document Title | REV. | Update/New/Optional | Submit Purpose | Submit Date | Approval Date | Remark
1. MANAGEMENT
2. PROCESS
1 | 1225 | D-113-1225-2001S | P&ID - UNIT 113 - SAMPLE CONNECTION DETAILS
3. MECHANICAL
4. PIPING
2 | 1360 | D-110-1360-0101S | STRESS CRITICAL LINE LIST
5. ELECTRICAL
3 | 1381 | D-U01-1381-0003S | SINGLE LINE DIAGRAM LOAD TABLE FOR LV MCC GROUP SS-U01 1 OF 4
4 | 1381 | D-U01-1381-0004S | SINGLE LINE DIAGRAM LOAD TABLE FOR LV MCC GROUP SS-U01 2OF4
5 | 1381 | D-U01-1381-0005S | SINGLE LINE DIAGRAM LOAD TABLE FOR LV MCC GROUP SS-U01 3OF4
6 | 1381 | D-U01-1381-0006S | SINGLE LINE DIAGRAM LOAD TABLE FOR LV MCC GROUP SS-U01 4OF4
7 | 1381 | D-M02-1381-0051S | EQUIPMENT LAYOUT SUBSTATION SS-M02
8 | 2181 | VS2181-012-A-U007 | GENERAL ARRANGEMENT FOR SSU01-MCC-401
9 | 2181 | VS2181-012-A-U008 | GENERAL ARRANGEMENT FOR SSU01-MCC-402
10 | 2181 | VS2181-012-A-U009 | GENERAL ARRANGEMENT FOR SSU01-MCC-403
11 | 2181 | VS2181-012-A-U010 | GENERAL ARRANGEMENT FOR SSU01-MCC-501
12 | 2181 | VS2181-012-A-U011 | GENERAL ARRANGEMENT FOR SSU01-DP-601
13 | 2181 | VS2181-012-A-U019 | SINGLE LINE DIAGRAM FOR SSU01-MCC-401
14 | 2181 | VS2181-012-A-U020 | SINGLE LINE DIAGRAM FOR SSU01-MCC-402
15 | 2181 | VS2181-012-A-U021 | SINGLE LINE DIAGRAM FOR SSU01-MCC-403
16 | 2181 | VS2181-012-A-U022 | SINGLE LINE DIAGRAM FOR SSU01-MCC-501
17 | 2181 | VS2181-012-A-U023 | SINGLE LINE DIAGRAM FOR SSU01-DP-601
18 | 1381 | D-000-1381-0200V | OVERALL PMS BLOCK DIAGRAM (UPDATING FOR STG6)
19 | 1381 | D-000-1381-0201PH | PMS BLOCK DIAGRAM FOR (UPDATING FOR STG6)
20 | 1382 | D-110-1382-0001S | OVERALL BREAKDOWN POWER LAYOUT STEAM & POWER AREA UNIT 110/111/112/113 (UPDATING FOR STG6)
21 | 1382 | D-110-1382-0003S | POWER LAYOUT STEAM & POWER UNIT 110/111/112/113 (2 OF 21)
22 | 1382 | D-110-1382-0006S | POWER LAYOUT STEAM & POWER UNIT 110/111/112/113 (5 OF 21)
23 | 1382 | D-110-1382-0052S | TRENCH AND CONDUIT LAYOUT STEAM & POWER UNIT 110/111/112/113 (UPDATING FOR STG6)
24 | 1382 | D-110-1382-0053S | TRENCH AND CONDUIT LAYOUT STEAM & POWER UNIT 110/111/112/113 (2 OF 15)
25 | 1382 | D-110-1382-0056S | TRENCH AND CONDUIT LAYOUT STEAM & POWER UNIT 110/111/112/113 (5 OF 15)
26 | 1382 | D-110-1382-0058S | TRENCH AND CONDUIT LAYOUT STEAM & POWER UNIT 110/111/112/113 (7 OF 15)
27 | 1382 | D-110-1382-0059S | TRENCH AND CONDUIT LAYOUT STEAM & POWER UNIT 110/111/112/113 ( 8 OF 15)
28 | 1382 | D-110-1382-0081S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113 (UPDATING FOR STG6)
29 | 1382 | D-110-1382-0082S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
30 | 1382 | D-110-1382-0083S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
31 | 1382 | D-110-1382-0085S | CABLE TRENCH SECTION LAYOUT STEAM & POWER UNIT 110/111/112/113
32 | 1382 | D-110-1382-0086S | CABLE TRENCH SECTION LAYOUT STEAM & POWER UNIT 110/111/112/113
33 | 1382 | D-110-1382-0087S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
34 | 1382 | D-110-1382-0088S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
35 | 1382 | D-110-1382-0089S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
36 | 1382 | D-110-1382-0090S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
37 | 1382 | D-110-1382-0091S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
38 | 1382 | D-110-1382-0095S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
39 | 1382 | D-110-1382-0120S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
40 | 1382 | D-110-1382-0127S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
41 | 1382 | D-110-1382-0128S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
42 | 1382 | D-110-1382-0129S | CABLE TRENCH SECTION LAYOUT STEAM & POWER AREA UNIT 110/111/112/113
43 | 1383 | D-110-1383-0001S | LIGHTING & SMALL POWER LAYOUTS TEAM & POWER AREA UNIT 110/111/112/113 (UPDATING FOR STG6)
44 | 1383 | D-110-1383-0035S | LIGHTING & SMALL POWER LAYOUTS STEAM & POWER AREA UNIT 110/111/112/113 (35 OF 102)
45 | 1383 | D-110-1383-0041S | LIGHTING & SMALL POWER LAYOUTS STEAM & POWER AREA UNIT 110/111/112/113 (41 OF 102)
46 | 1383 | C-110-1383-1001PH | LIGHTING ILLUMINATION CALCULATION FOR STG6
47 | 1384 | D-110-1384-0001S | OVERALL BREAKDOWN EARTHING & LIGHTNING LAYOUT STEAM & POWER UNIT UNIT 110/111/112/113 (UPDATING FOR STG6)
48 | 1383 | C-110-1383-0001 | LIGHTING ILLUMINATION CALCULATION FOR STG6
49 | 1381 | D-U01-1381-0051S | EQUIPMENT LAYOUT SUBSTATION SS-U01 (UPDATING FOR STG6)
50 | 1381 | D-U01-1381-0061PH | EQUIPMENT INSTALLATION LAYOUT SUBSTATION SS-U01 (UPDATING FOR STG6)
51 | 1382 | D-U01-1382-0001S | POWER LAYOUT SUBSTATION U01
52 | 1382 | D-U01-1382-0044S | CABLE TRAY LAYOUT SUBSTATION U01 (U/G TRENCH OVERALL) (UPDATING FOR STG6)
53 | 1382 | D-U01-1382-0046S | CABLE TRAY LAYOUT SUBSTATION U01 (LV U/G TRENCH) (UPDATING FOR STG6)
54 | 1382 | D-U01-1382-0201S | CONNECTION LIST - SUBSTATION SS-U01
55 | 1382 | D-U01-1382-0101S | ELECTRICAL CABLE SCHEDULE FOR SS-U01
56 | 1382 | D-M02-1382-0201S | CONNECTION LIST - SUBSTATION SS-M02
6. INSTRUMENTATION
36 | 1370 | D-113-1370-0801S | LOOP DIAGRAM & DETAIL (UNIT 113)
37 | 1378 | D-113-1378-0001S | TYPICAL INSTRUMENT INSTALLATION DETAIL (STG UNIT-113)
38 | 1378 | D-113-1378-0303S | CABLE SCHEDULE & DETAIL (UNIT 113)
39 | 1223 | S-113-1223-0801S | CAUSE AND EFFECT DIAGRAM (UNIT 113)
40 | 1370 | S-113-1370-1001S | INSTRUMENT INDEX & DETAIL (UNIT 113)
41 | 1370 | S-113-1370-1002S | SIL RELIABILITY CALCULATIONS (UNIT 113)
42 | 1373 | S-113-1373-0101S | DATASHEET FOR ELECTRIC TRANSMITTER (UNIT 113)
43 | 1373 | S-113-1373-0401S | DATA SHEET FOR TEMPERATURE ELEMENTS AND WELLS
44 | 1373 | S-113-1373-0502S | DATASHEET FOR THERMOMETER AND WELL (UNIT 113)
45 | 1373 | S-113-1373-0601S | DATA SHEET FOR ORIFICE PLATES
46 | 1373 | S-113-1373-0602S | DATA SHEET FOR VENTURI TUBE
47 | 1374 | S-113-1374-0201S | DATA SHEET FOR BALL TYPE ON-OFF VALVES
48 | 1375 | S-113-1375-0101S | DATA SHEET FOR ANALYZER
49 | 1375 | S-113-1375-0301S | DATASHEET FOR F&G DETECTOR (UNIT 113)
50 | 1378 | S-113-1378-1001S | NAMEPLATE LIST FOR INSTRUMENT (UNIT 113)
51 | 1371 | C-B40-1371-0702S | IS CIRCUIT VERIFICATION
52 | 1378 | D-B40-1378-0101S | INSTRUMENT LAYOUT DRAWING KEY PLAN (STEAM & POWER GENERATION UNIT-110/112/113)(FGD UNIT-111)
53 | 1378 | D-B40-1378-0201S | INSTRUMENT CABLE TRENCH LAYOUT & DETAIL (B400)
54 | 1378 | D-B40-1378-0301S | INSTRUMENT CABLE TRAY LAYOUT & DETAIL (B400)
55 | 1378 | D-B40-1378-0302S | INSTRUMENT MAIN CABLE LAYOUT & DETAIL (B400)
56 | 1378 | D-B40-1378-0503S | INSTRUMENT AIR PIPING LAYOUT & DETAIL (B400)
57 | 1382 | D-I12-1382-0001S | POWER LAYOUT INSTRUMENT SATELLITE BUILDING ISB-12
58 | 1382 | D-I12-1382-0041S | POWER TRAY INSTRUMENT SATELLITE BUILDING ISB-12
59 | 1381 | D-I12-1381-0051S | EQUIPMENT INSTALLATION LAYOUT ISB-12
60 | 1381 | D-I12-1381-0061S | EQUIPMENT INSTALLATION LAYOUT ISB-12
61 | 1360 | S-113-1360-0501S | DATA SHEET FOR PRESSURE RELIEF VALVE
62 | 1360 | S-113-1360-0504S | DATA SHEET FOR RESTRICTION ORIFICE
55 | 1378 | D-000-1378-0501V_4 | ﻿Typical Instrument Air Line Hook-up Drawing
56 | 1378 | D-000-1378-0501S_1 | ﻿Instrument Air Line Hook-up Drawing
57 | 1378 | D-000-1378-0501M_1 | ﻿Instrument Air Line Hook-up Drawing
58 | 1378 | D-000-1378-0401V_2 | ﻿Typical Instrument Impulse line Hook-up Drawing
59 | 1378 | D-000-1378-0401S_1 | ﻿Typical Instrument Impulse line Hook-up Drawing
60 | 1378 | D-000-1378-0401M_1 | ﻿Instrument Impulse Line Hook-up Drawing
61 | 1378 | D-000-1378-0401J_2 | ﻿Typical Instrument Impulse Line Hook-up Drawing
62 | 1378 | D-000-1378-0401G_2 | ﻿Typical Instrument Impulse Line Hook-up Drawing
63 | 1378 | D-000-1378-0311V_0 | Typical Cable tray layout
64 | 1378 | D-000-1378-0301V_0 | Typical Cable Schedule
65 | 1378 | D-000-1378-0501G_1 | ﻿Instrument Air Line Hook-Up Drawing
66 | 1378 | D-000-1378-0101V_1 | Typical Instrument Location plan
67 | 1378 | D-000-1378-0001V_6 | ﻿Typical Instrument Installation Drawing
68 | 1378 | S-000-1378-0004V_2 | ﻿Instrument Design and Installation Specification
69 | 1378 | S-000-1378-0003V_2 | ﻿Specification For Instrument Bulk Materials
70 | 1378 | S-000-1378-0002V_4 | ﻿Specification For Instrument Junction Boxes
7. CIVIL & STRUCTURE
71 | 1315 | D-000-1315-1011V | STANDARD CABLE TRENCH SECTIONS (UPDATING FOR STG6) | X
72 | 1315 | D-000-1315-1012V | STANDARD PIPE TRENCH SECTIONS (UPDATING FOR STG6) | 9
73 | 1315 | D-000-1315-1013V | STANDARD CABLE TRENCH CROSSING RULE (UPDATING FOR STG6) | 2
74 | 1315 | D-000-1315-1101V | TYPICAL UNDERGROUND INSTALLATION DETAILS FOR COOLING WATER AND SEA WATER PIPELINES (UPDATING FOR STG6) | 2
75 | 1315 | D-AC0-1315-0001C | ELECTRICAL & INSTRUMENT CABLE TRENCH LAYOUT (UPDATING FOR STG6)
76 | 1315 | D-AC0-1315-0007C | ELECTRICAL CABLE TRENCH CUTOUT BOX SCHEDULE (UPDATING FOR STG6)
77 | 1315 | D-AC0-1315-0008C | ELECTRICAL CABLE TRENCH, CABLE PULL PIT SCHEDULE AND DETAILS (UPDATING FOR STG6)
78 | 1323 | C-B40-1323-0281S | ASSESSEMENT FOR FOUNDATION OF STG6
79 | 1323 | D-B40-1323-0001S | FOUNDATION LOCATION PLAN FOR STEAM & POWER AREA (1)
80 | 1323 | D-B40-1323-0006S | PIPE LOCATION PLAN FOR STEAM & POWER AREA (1)
81 | 133A | C-B40-133A-4201S | STRUCTURAL CALCULATION FOR FOUNDATION OF STG 6
82 | 133A | D-B40-133A-2209S | STEAM TURBINE GENERATOR SHELTER-STG6 EQUIPMENT FOUNDATION DETAILS
83 | 133A | D-B40-133A-2204S | STEAM TURBINE GENERATOR SHELTER-STG6 GROUND FLOOR BEAM & GIRDER RE-BAR DETAILS
84 | 133A | D-B40-133A-4101S | STEAM TURBINE GENERATOR SHELTER-3 GROUND FLOOR & P/F PLANS & MEZZ. FLOOR PLAN
85 | 133A | D-B40-133A-4102S | STEAM TURBINE GENERATOR SHELTER-3 TOF EL+112.025~115.025 FLOOR PLAN & CRANE GIRDER & ROOF PLAN
86 | 133A | D-B40-133A-4103S | STEAM TURBINE GENERATOR SHELTER-3 ELEVATIONS-1
87 | 133A | D-B40-133A-4105S | STEAM TURBINE GENERATOR SHELTER-3 MAIN SECTIONS
88 | 133A | D-B40-133A-4106S | STEAM TURBINE GENERATOR SHELTER-3 WALL SECTIONS
89 | 133A | D-B40-133A-4107S | STEAM TURBINE GENERATOR SHELTER-3 MISC DETAILS
90 | 133A | D-B40-133A-4201S | STEAM TURBINE GENERATOR SHELTER-3 FOUNDATION & PILE LOCATION PLAN & COLUMN ARRANGEMENT PLAN
91 | 133A | D-B40-133A-4202S | STEAM TURBINE GENERATOR SHELTER-3 FOUNDATION RE-BAR DETAILS
92 | 133A | D-B40-133A-4203S | STEAM TURBINE GENERATOR SHELTER-3 FOUNDATION RE-BAR DETAILS-2
93 | 133A | D-B40-133A-4301S | STEAM TURBINE GENERATOR SHELTER-3 COLUMN ARRANGEMENT PLAN & BASE PLATE DETAILS
94 | 133A | D-B40-133A-4302S | STEAM TURBINE GENERATOR SHELTER-3 MEZZ. FLOOR FRAMING PLAN
95 | 133A | D-B40-133A-4306S | STEAM TURBINE GENERATOR SHELTER-3 FRAMING ELEVATIONS-3
96 | 133A | D-B40-133A-4307S | STEAM TURBINE GENERATOR SHELTER-3 STAIR PLAN & SECTION
97 | 133A | D-B40-133A-4308S | STEAM TURBINE GENERATOR SHELTER-3 CRANE GIRDER ENLARGED PLAN & DETAILS
98 | 133A | D-B40-133A-4309S | STEAM TURBINE GENERATOR SHELTER-3 CONNECTION DETAILS-1
99 | 133A | D-B40-133A-4310S | STEAM TURBINE GENERATOR SHELTER-3 CONNECTION DETAILS-2
100 | 133A | D-B40-133A-4311S | STEAM TURBINE GENERATOR SHELTER-3 CONNECTION DETAILS-3