## Sheet1
INSPECTION AND TEST PLAN
| R: Review | SW: Spot Witness | W: Witness | H: Hold point
No. | Inspection Item | Inspection Involvement
|  | PURCHASER | OWNER | 3rd Party Inspection
1 | Material certificates | R | R | R
2 | CO/CQ | R | R | -
3 | Material identification | SW | R | R
4 | Balancing Test (impeller) | - | - | -
5 | Heat Treatment | - | - | -
6 | PMI (where applicable) | R | R | -
7 | Hydrostatic Testy | W | SW | W
8 | Helium leak Test (if required) | R | R | -
9 | Dimensional check and visual inspection | W | SW | W
10 | N.D.E (***) | - | - | -
11 | NPSH Test (if required) | - | - | -
12 | Mechanical running test (*) - Noise, Vibration, Temp. rising check, RPM, etc. | - | - | -
13 | Performance Test (*) - Capacity, Head, BHP, Efficiency | - | - | -
14 | Dismantling inspection (where required) | - | - | -
15 | Motor Inspection (**) | - | - | -
16 | Internal cleaning inspection | W | W | -
17 | Component and Accessories inspection | SW | R | -
18 | Final assembly inspection | SW | R | -
19 | Rust prevention check and painting inspection | SW | R | R
20 | Shipping preparation inspection | SW | R | -
21 | Certificate of Completion and Final vendor inspection report review | R | R | R
Notes:
(*) One pump per each identical pump.
(All pumps will be witness tested for critical & big size pump)
(**) Electric Motor inspection detail shall be indentified later
(***) NDE shall be done after 24hrs from welding work and 48hrs from PWHT